## Summary
(Confidential)
Customer | Fujitsu (Thailand) Co., Ltd.
Project | ITOP
Document | Q&A

## Issue
No. | Type | Priority | Function | Description | Reference | Feedback | Created Date | Lastest Date | Note
1 | QA | Very High | Main Menu Screen | About overall information | Sheet1 |  | 2023-01-04
2 | QA | Very High | Main Menu Screen | Default information on the Initiation page | Sheet2 |  | 2023-01-09
3 | QA | High | Snapshot Report | How to validate timestamp value? | Sheet3 |  | 2023-01-10
4 | QA | High | Generate Report | The default query in the document is missing | Sheet4 |  | 2023-01-10
5 | QA | Nomal | Custom Report | There is no VIN field on "Report Monitoring" Screen | Sheet5 |  | 2023-01-10
6 | QA | Nomal | Monitoring Report | Confirmation about Search conditions and download reports | Sheet6 |  | 2023-01-10
7 | QA | Nomal | Snapshot Report | Get address from Google API | Sheet7 |  | 2023-01-10

## Sheet1
Issue
1 | How to retrieve overall information (4 fields). (number of the vehicle, number of the impacted vehicle, etc.)
ANS Count Record from CUSTOMER_VEHICLE which delete
(Delete Flag is not exists)
2 | Is there any other information besides this?
Could you please explain this to me?

## Sheet2
Issue
1 | About the colors on the report, I am also doing the same as the document you sent. This function on the web cannot be changed manually.
1.1 | Can I change these colors to be suitable for the website theme?
ANS Base by below, It is OK
1.2 | Do you need to manually adjust this color?
ANS If customer is ok with this colortheme, It is no need to manually change. it will fixed by that color
2 | The snapshot report will be exported to excel according to the available excel template
2.1 | Are the colors and layout (at this function on the web) required to be the same as the excel template?
ANS Please make it similar, but may not excatly the same, but base by below of On Web look. It is ok.
2.2 | If the excel template has been changed, does this function on the web reflect that automatically?
In my opinion, it is not necessary. Please confirm.
ANS Yes, It is not neccessary. Actually Template should not bechange after we go-live. If there is request to change, We need to estimate again.
3 | About Request ID field
3.1 | How is the format of the "Request ID"?
Is the format "user yyyyMMddhhmmss" ok?
ANS Let's me Confirm About this
3.2 | I think the "Request ID" here is unnecessary. It will be generated automatically on the request report screen and displayed on the "Report Monitoring" screen.
Please explain more. Thank you.
ANS Let's me Confirm About this, but I think it is not necessary
| On Web look like | Snapshot Report in Excel

## Sheet3
Issue
About validate timestamp
1 | I understand that: Timestamp is VALID if the value matches the pattern in the correct format yyyyMMddhhmmss.
Please confirm for me. Thanks!
ANS Invalid TimeStamp is Timestamp start with 2106XXXX

## Sheet4
Issue
1 | In ITO Tool Mapping, Sheet DEALER_WARINING, The specification for default query is missing.
Please add more information.
Ans Please let's me Confirm

## Sheet5
Issue
1 | In the "Generate Report" screen, there is no VIN field. so, when the request displayed on the "Report Monitoring" screen, the VIN column will be empty
Please confirm this point.
Ans For Customer Report, Please set it as blank.
Dữ liệu đăng ký từ màn hình Custome Report sẽ có VIN = EMPTY ?

## Sheet6
Issue
1 | I think Search condition "Request Data" should have 2 inputs "From Date" - "To Date"
Mandatory input fields: only "Request Data"
Ans For this, It allow only see data only for 1 day. From To may cause slow performace if period is too big. (Mostly user will see data that generate today.)
2 | In column Management: When all reports are completed, the link "Completed" will be active.
Users click this link to download all reports in 1 zip file.
Do you have any idea? Please let me know.
ANS They want to seperate becasue they can download some report to continue their work first. No need to wait for all report.
but after finish you can make as 1 ZIP in Management column for download all that is ok also.

## Sheet7
Issue
1 | The address gets via Google API which is paid service.
Please concern about this point. If you have any changes to this requirement, please let me know soon.
ANS Let's me confirm about this since current this one is get from google map.